Golimumab Implementation Checklist

Phase 1 Purpose: This phase of the checklist is designed to support planning 4-6 months prior to MPSC framework start date.  Pharmacy teams are encouraged to engage with clinical leads to initiate discussions regarding moving to best value medicines and identifying potential barriers.  This allows enough time for informing patients and overcoming any challenges in implementing.

| Phase 1: Pre-Framework Award |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Task/Action | Person/Team Responsible | In Progress (Date) | Comments/Updates/Decisions | Completed (Date) |
| 1 | Identify and appoint a dedicated implementation lead and clinical champion(s). |  |  |  |  |
| 2 | Engage and seek input from across all clinical specialties as appropriate; predominantly rheumatology and gastroenterology. |  |  |  |  |
| 3 | Identify how the medicine is funded in your organisation and engage with commissioner (finance, medicines optimisation and contract teams) to support with implementation where required. |  |  |  |  |
| 4 | Identify number of patients currently being treated with the medicine and how they are supplied, golimumab is predominantly supplied through homecare. |  |  |  |  |
| 5 | Review and agree which patients will be eligible for moving to a best value biologic. |  |  |  |  |
| 6 | Liaise with homecare providers to understand their processes for managing the switch (whether you plan to stay with current provider or move providers). |  |  |  |  |
| 7 | Discuss and agree prescription lengths with clinical teams considering the framework start date of 1st November 2025 |  |  |  |  |
| 8 | Consider how patients will be informed and/or consented. Consider new patient starts and how you will include consent to adopting a best value golimumab in the future (de-branding consent) |  |  |  |  |
| 9 | Consider an appropriate patient awareness campaign and agree how this will be delivered. Trust may choose to deliver this in clinic or through homecare providers ahead of implementation. |  |  |  |  |
| 10 | If you have any stock in pharmacy or OPD providers consider how this will be used and make necessary adjustments to your pharmacy system to prevent unnecessary reordering. |  |  |  |  |